## Daily Log
Date | Day | Sprint # | Task # (per day) | Task / User Story | Category | Description of Work Done | Hours Spent | Status | Blockers / Notes | Deliverable / Output
2026-05-04 | Monday | 1 | 1 | refactor code and bug fix | Development | Updated frontend UI/UX to show toast events: success toast on successful Apex call, success toast with workflow end status when ticket workflow completes, and error toast using standard error-handling strategy for failures. | 2 | Done |  | branch : manage_ticket_page ------------------------------------------ commit :[fce793aaffa41e98ce7a31d834f4780ebf7cf585] ------------------------------------------
2026-05-04 | Monday | 1 | 2 | refactor code and bug fix | Development | Implemented conditional CSS styling on ticketBoardColumn (child LWC) based on workflow end status received from manageTicketTracking (parent LWC) after an Apex callout that updates ticket status. Refactored the data contract so the state object passed from parent to child includes both entity fields and calculated fields (e.g. endStatus) instead of passing the flag as a separate property — keeps the API clean and avoids prop drilling. Since LWC doesn't support dynamic className binding on a child component's internal container from the parent (parent only controls the root element's class), applied the styling via a data-end-status HTML attribute on the child's container and targeted it in CSS with the attribute selector .ticket-card[data-end-status="true"]. | 0.5 | Done |  | notepad_rule_file :how_child_know_style_basedonpatherstate ----------------------------------------- branch : manage_ticket_page ----------------------------------------- commit : [34c1c058530a1749cdc087ce6f35ac8b9b304d88]
2026-05-04 | Monday | 1 | 3 | add Ticket Link To | Development | in the right page requirement 1- add the main action to show the ticket link 2- add usecase documentation for this action 3- add the request api 4- add the dto 5- add the sequence for the backEnd lifeCycle Say who own the pop up describe how the pop up looks like describe the frontEnd flow and component communication describe how the call should be done :(@wire and describe how we should work with @ wire : framework detail) | 2 | Done | blocked until 8 end | branch : manage_ticket_page ------------------------------------------ commit :[ { 7c8f41af75042c1b442a762c4302179f9573c30b, manually} , { 05ba22fdea6c95581a00eb21c2642c604644fc44, P013 } ] with the previous commit also manually created ------------------------------------------
2026-05-05 | Monday | 1 | 4 | when a sprint is started I cant clicked it again (BUG) | Development |  |  | Not Started | blocked until 8 end
2026-05-05 | Monday | 1 | 5 | As a user I want to see the total story point completed , total story point uncompleted and total story points for each sprint | Development |  |  | Not Started | blocked until 8 end
2026-05-05 | Monday | 1 | 6 | Create a excel file for prompt study | Other |  | 1.12 | Done |  | file : prompt_study
2026-05-05 | Monday | 1 | 7 | Problem 1 is about consistency — the container and the child live in different places in the DOM(different lwc) but must change shape together, so one of them can't decide independently. Problem 2 is about the second parent breaking the assumption that screen size is what drives everything — it always wants cards, and it needs them smaller, which variant = "row" ¦ "card" alone can't express. | Planning | Solution 1 answers: "who owns the decision?" — the parent owns it once, and both the container class and the child prop react to the same value. Neither the container nor the child makes an independent decision about screen size. Solution 2 answers: "what if the trigger is different per parent?" — by splitting variant into shape and size, each parent only controls what it actually knows about. Parent 1 knows about screen size so it sets shape. Parent 2 knows it lives in a tight column so it sets size = compact. The child just renders whatever combination it receives, without caring where it came from. Found the right prompts for my case | 3 | Done | Cannot mark as completed until see result of #Task 8 | file : lwc_tow_problems.svg --------------------------------------- Found the right Group of prompts [ P003: {branch : manage_ticket_page commit : 4b17418667db0275a3d8a4de22240a6b345d3bcc}, P004:{branch: manage_ticket_page, commit: af86d0c0e08907aae8c1958132891d2cee267357}, P005{branch : manage_ticket_page, commit : d0ca35292af2db81abf475b1ed96fa580dc9f049} ]
2026-05-05 | Monday | 1 | 8 | BUG: in Ticket Tracking page when we load the page and a ticket have hit the endStatus of the assigned workflow to it s type : It does not show as that . | Development |  | 1 | Done |  | 5/5/2026-task6-G002-[P006-P007-P008] branch : manage-ticket_page commit : 4587551c9913647c93a7a82d5934169d19c2761d
2026-05-05 | Monday | 1 | 9 | BUG : assignee field is not showed for ticket tracking | Development |  |  | Done
2026-05-06 | Tuesday | 1 | 10 | BUG : ticket type value is not showed | Development | Time to found problem : 10 min, Time to solve the problem with test : 10 min, Time commit + push + update prompt text and set the tas done : 10 min | 0.2 | Done |  | branch : manage_ticket_tracking commit : ae26070df27f40cbe4d9d46dfa0c085b6099cb9c
|  |  | 11 | ticket link | Development |  | 2 | Done |  | branch : manage_ticket_tracking commit : 7c8f41af75042c1b442a762c4302179f9573c30b
|  |  | 12 | Plan to change end status | Planning | `- update er TASK 13 - update erd TASK 14 - plan for the development change TASK 15 | 0.3 | Blocked | TASK 13 TASK 14
|  |  | 13 | UPDATE ER | Design | A PROJECT SHOULD HAVE A SINGLE START STATUS. A PROJECT SHOULD HAVE A SINGLE END STATUS. | 0.1 | Done |  | branch : manage_ticket_tracking commit hash : 501b221833fc2b4d09bc60bf11577d8c8379bb5c commit message : watch blue change in new_er_diagram or Untitled Diagram-Page2.drawio.png
|  |  | 14 | UPDATE ERD | Design | FOLLOWING THE ER RELATIONSHIP: A project has many statuses, but it must also have exactly one Start Status and one End Status. PROBLEM: If we store `startStatusId` and `endStatusId` directly in the `Project` table, this creates double coupling between `Project` and `Status`: * `Project` already owns multiple `Status` records (1-to-many) * Adding `startStatusId` and `endStatusId` creates extra direct references back to `Status` This design can become harder to maintain and unnecessarily increases structural complexity. SOLUTION 1: Normalize using a Many-to-Many (M:N) relationship A separate mapping structure could be created to define special status roles such as Start and End. DRAWBACK: This approach is too complex for a simple requirement where each project only needs: * One fixed Start Status * One fixed End Status SOLUTION 2: Add flags inside `Status` Add: * `isStart` * `isEnd` This keeps the structure simpler, but introduces integrity and security risks because users could: * Modify the flags later * Create multiple Start or End statuses for the same project REQUIRED DATABASE PROTECTION (TRIGGERS): 1. Project Creation Trigger * Automatically create default statuses when a project is created: * `Todo` with `isStart = true` * `Done` with `isEnd = true` 2. Status Update Trigger * Prevent updates to `isStart` and `isEnd` after creation 3. Status Insert Trigger * If a new status has `isStart = true`, verify that no other Start status already exists in that project * If a new status has `isEnd = true`, verify that no other End status already exists in that project FINAL RESULT: This ensures: * Exactly one Start Status per project * Exactly one End Status per project * No duplicate flagged statuses * Strong integrity enforcement * Simpler ER design without unnecessary normalization complexity | 0.3 | Blocked | TASK 15
|  |  | 15 | plan for the development change | Planning | Found the previous code that is affected : - DomainCompleteValidator : isEndStatus - TicketService : changeTicketState - ManageTicketTrackingController - ManageBacklogController - manageTicketTracking.js : _loadData method | 0.4 | Blocked | Task 16 | commit hash : 35b63489ea349ff172c16329adc6603cc1a7256f commit message : 5/7/2026-sprint1-[task15-task16]
|  |  | 16 |  | Development | P014 - P015 - P016 | 0.3 | Done |  | commit hash : 35b63489ea349ff172c16329adc6603cc1a7256f commit message : 5/7/2026-sprint1-[task15-task16]

## Sprint Plan
Sprint # | Goal / Theme | Start Date | End Date | Duration (days) | Status
1 | Sprint 1 goal — describe here | 2026-05-04 | 2026-05-17 | 14 | Not Started
2 | Sprint 2 goal — describe here | 2026-05-18 | 2026-05-31 | 14 | Not Started
3 | Sprint 3 goal — describe here | 2026-06-01 | 2026-06-14 | 14 | Not Started
4 | Sprint 4 goal — describe here | 2026-06-15 | 2026-06-28 | 14 | Not Started
5 | Sprint 5 goal — describe here | 2026-06-29 | 2026-07-12 | 14 | Not Started
6 | Sprint 6 goal — describe here | 2026-07-13 | 2026-07-26 | 14 | Not Started

## Summary
Project Summary
Total hours logged | 13.22
Total tasks logged | 15
Distinct days worked | 3
Avg tasks per day | 5
Avg hours per day | 4.4067
Tasks Done | 11
Tasks In Progress | 0
Tasks Blocked | 3
Completion % | 73.33%
Hours by Category |  | Hours by Sprint
Planning | 3.7 | Sprint 1 | 9.82
Design | 0.4 | Sprint 2 | 0
Development | 8 | Sprint 3 | 0
Testing | 0 | Sprint 4 | 0
Documentation | 0 | Sprint 5 | 0
Meeting | 0 | Sprint 6 | 0
Research | 0
Setup | 0
Deployment | 0
Other | 1.12